## Risks log
| Date updated | Type |  | Consequence | Likelihood | Impact | Mitigation
Example | 13.8.2020 | Project | Cannot collaborate in person due to COVID-19 | Do not fully benefit from learning from eachother. Everything takes a lot longer. | M | M | Meet in our houses if permitted. Utilisation of Zoom and other online collaboration tools.
Example | 15.9.2020 | Project | Conflicting feedback | Difficulty in making updates as not clear on which stakeholders to prioritise | M | L | Keep a track of feedback via feedback log
Example | 30.9.2020 | Technology | Component failure | Not having a working prototype for Demo Day | M | H | Identify which parts are most important (and most likely to break) and buy backups

## Feedback log
Intent, Method, Scale/Scope, Risks
| ID | Status | Feedback | Source | Date | Action taken /Outcome | Type of feedback | Comments / furthe detail
Example | 7 | Open | concerned about usability / audience / commerciality of the tap | Katherine | 2020-08-10 | To be revisited later on, particularly through pathways to scale | Scale + Risks
Example | 14 | Closed | Stakeholders - include industrial organisations | 3AI Panel - Design Brief | 2020-08-13 | Included an understanding of relevance of tap to industrial organisations through conversation with Ernesto Rodrigo Leal & Burgmann College | Method
Example | 31 | Closed | Replace stepper motor with servo motor | Ernesto Rodriguez Leal | 2020-10-08 | We will do some building with this in parallel, but note that there is a lot of benefit to stepper motor if we could get it to work as we would be able to use with a needle valve which has more degrees of opening potential. In the end we did not need to go down this path | Method | This is suggested in order to have more control/torque and to avoid the issue of not knowing where the stepper motor is in reality (as it misses steps).

## Decisions made
| Date | Overview | Decision -made | Explicit? | Rationale
Example | 2020-07-29 | HuskyLens Components | We will use HuskyLens for computer vision + AI | Yes | Simplest to operate, good with household objects
Example | 2020-08-12 | Language / concepts - focus on water flow | Water flow and not water pressure | Yes | From speaking with JD
Example | 2020-09-01 | Stepper motor - need bipolar | Tried to connect the stepper motor to the controller board we bought. Turns out we bought a unipolar stepper motor, and a controller for a bipolar motor. Agreed to purchase a bipolar stepper motor from Core Electronics rather than hack the unipolar stepper motor to fit with controller board we bought. | Yes | Functionality
Example | 2020-10-05 | Connect directly to the tap | Changed our mind for the demo - will connect tappy directly to the tap, using metal tap fittings we will purchase (instead of a bucket scenario) | Yes | Usefulenss